## Slide 1: Changing the way we 'Make Decisions'.
Abdi Segulle – Project Leader

## Slide 2: Pathways to Board Project - The Journey
Reality check!!! Most Boards are NOT diverse!
A shared commitment to develop greater diversity on Boards

## Slide 3: Pathways to Board Project - The Journey
Identify Placement Training Mentoring Shadowing Interviewing Appoint Onboarding Support
The first step to identify potential board members through the founding members and beyond
After identifying the potential board members, we will select potential board members and process their details and agree for them to start the program
We will identify the training program and agree dates of delivery and location
We will identify suitable mentors for individuals and dates to introduce them to their mentors
In conjunction with the mentoring we will arrange shadowing for individuals to sit and observe existing board sessions
After everyone completes the program, we will arrange mock exams for individuals to prepare for board interviews
Once an individual is successful to join a board, we will support them for 6 months

## Slide 4: Pathways to Board Project – Training Schedule - 2022
The Role of Board
March
Mentoring
Shadowing
Treasury Management
Leadership
May
Mentoring
Shadowing
Confidence Building
Internal Auditing
April
Mentoring
Shadowing
External Auditing
Interview Techniques
June & July
Mentoring
Shadowing
Mock Interview Sessions
Hugh James
TBC
Mazars
Centris
TBC
TBC
TBC
Mazars
Academy Wales
TBC
In-house
In-house
TBC
TBC
TBC
Acorn Recruitment

## Slide 5: Pathways to Board Project – Shadowing Board Meetings
Every individual will have the opportunity to shadow Board sessions throughout the training program
Cohort will be able to join in the Board conversation or they can choose to observe
Project Leader will have a 1-1 sessions with the cohort during the program

## Slide 6: Pathways to Board Project – Mentoring
All the cohort will be allocated a mentor throughout the training program
They will at least one session per month – open to more if both mentor and individuals agree
The mentoring can go beyond the training both parties are happy with it

## Slide 7: Pathways to Board Project – Interview techniques – Mock interviews
Interview techniques training session
Mock interview sessions with professionals
Support with Applications for Board Roles

## Slide 8: Pathways to Board Project – Appoint & Onboard Support
Once appointed to a Board individuals will have access to six months onboard support